## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | Fix Spring Boot project build errors & crash issue | MUST | None | Kavya | Completed
Sprint 1 | Sprint 1 | US-002 | Add fields to Staff model after project head request | MUST | None | Kavya | Completed
Sprint 1 | Sprint 2 | US-003 | Fix Product model errors + resolve mapping issues | MUST | US-001 | Kavya | Completed
Sprint 1 | Sprint 2 | US-004 | Configure application.properties for H2 database | MUST | US-001 | Kavya | Completed
Sprint 2 | Sprint 3 | US-005 | Implement Product CRUD APIs (Create, View, Update, Delete) | MUST | US-003 | Kavya | In Progress
Sprint 2 | Sprint 3 | US-006 | Fix “Add Product” page issues & align with backend | MUST | US-005 | Kavya | Completed
Sprint 2 | Sprint 3 | US-007 | Build Inventory Home Page UI (saved version asked) | SHOULD | None | Kavya | Completed
Sprint 3 | Sprint 4 | US-008 | Modify View Products page with improved layout | SHOULD | US-005 | Kavya | Completed
Sprint 3 | Sprint 4 | US-009 | Footer design variations for project approval | COULD | None | Kavya | Completed
Sprint 3 | Sprint 4 | US-010 | Store Home Page HTML & Add Product HTML in project memory | MUST | None | Kavya | Completed
Sprint 4 | Sprint 5 | US-011 | Full line-by-line explanation of backend code for documentation | MUST | US-005 | Kavya | In Progress
Sprint 4 | Sprint 5 | US-012 | Write report sections: Testing Overview, Use Case points | MUST | None | Kavya | Completed
Sprint 4 | Sprint 5 | US-013 | Generate project diagrams (Use Case, Sequence, DFD, Deployment) | MUST | US-012 | Kavya | In Progress
Sprint 5 | Sprint 6 | US-014 | Fix issues while generating report PDF (formatting + headings) | SHOULD | US-012 | Kavya | Completed
Sprint 5 | Sprint 6 | US-015 | Add multilingual content (Tanglish instructions) per user need | COULD | None | Kavya | Completed
Sprint 6 | Sprint 7 | US-016 | Complete remaining report sections (Existing System, Conclusion) | MUST | US-012 | Kavya | Pending
Sprint 6 | Sprint 7 | US-017 | Review full Inventory System flow before final submission | SHOULD | All previous | Kavya | Pending
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7