## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Kavya | 2025-11-17 | Spring Boot project failed to start due to missing dependency & config issue | Sprint 1 | Kavya | Backend Build Defect | Added missing dependencies, fixed config | 2025-11-17 | Closed | App started successfully
2 | Kavya | 2025-11-17 | Product model fields created incorrectly, causing POST API failure | Sprint 1 | Kavya | Backend Logical Defect | Updated Product model fields, fixed mapping | 2025-11-18 | Closed | POST API now working
3 | Kavya | 2025-11-18 | H2 database not showing data due to incorrect properties | Sprint 1 | Kavya | Configuration Defect | Corrected application.properties settings | 2025-11-18 | Closed | H2 console working
4 | Kavya | 2025-11-19 | Add Product form UI misalignment & button not centered | Sprint 2 | Kavya | UI/UX Defect | Corrected CSS & alignment | 2025-11-19 | Closed | UI looks clean now
5 | Kavya | 2025-11-20 | View Products page table overlapping content | Sprint 2 | Kavya | UI Layout Defect | Redesigned table layout | 2025-11-20 | Closed | Page displays properly
6 | Kavya | 2025-11-20 | Staff model update caused minor application restart warning | Sprint 2 | Kavya | Backend Structural Defect | Rebuilt model, regenerated project | 2025-11-20 | Closed | Stable
7 | Kavya | 2025-11-21 | Update Product API not reflecting updates properly | Sprint 3 | Kavya | API Defect | Backend logic updated; UI update pending | 2025-11-24 | Partially Closed | Backend OK, UI pending
8 | Kavya | 2025-11-22 | Product Delete function not available in UI | Sprint 3 | Kavya | Missing Functionality | Planned for next sprint | Pending | Open | Delete feature not implemented
9 | Kavya | 2025-11-23 | Login page buttons not styled consistently | Sprint 3 | Kavya | UI/UX Defect | Updated CSS styling | 2025-11-23 | Closed | Uniform design achieved
10 | Kavya | 2025-11-24 | Report diagram clarity low (Use Case/Sequence) | Sprint 4 | Kavya | Documentation Defect | Regenerated diagrams in HD | 2025-11-24 | Closed | HD diagrams delivered
11 | Kavya | 2025-11-25 | PDF formatting issues (colors, heading, Tanglish mix) | Sprint 4 | Kavya | Documentation/Layout Defect | Corrected formatting template | 2025-11-25 | Closed | Ready for export
12 | Kavya | 2025-11-26 | Existing System & Testing sections incomplete in report | Sprint 5 | Kavya | Documentat

## Sheet2
Logical
User Interface
Maintainability
Standards
Others